## Sheet1
ID | Type | Description | Source | Impact if incorect / unresolved | Validation Method | Owner | Target Date | Status | Related Artifact
A-001 | Assumption | There is power to the school | RFI | The project will be on hold or fail till power is ran to building | Site walk through | Senior Infrastructure Lead | TBD | Open | Design
A-002 | Assumption | School is range of Cell Towers | RFI | If terrestrial or cellular service is unavailable, POS-Networking must evaluate LEO or other connectivity alternatives, affecting cost and lead time. | GIS survey / Follow Up | GIS Surveyer | 2026-09-06 | Open | Design / Budget
Q-001 | Open Question | When does the project have to start and by |  | This will effect scheduling of recouses / Budget Impact | Follow up | Project Coordinator | 2026-09-06 | Open | Schedule
C-001 | Constraint | Building 150 Mieters apart | RFI | We will need to use Wifi Signal or Fiber in designe / Budget impact | Confirmed | Network Engineer | 2026-09-08 | Open | Design / Budget
R-001 | Requirement | Network must support 150 users | RFI | Will need to be accounted for in design / procurment estimates | Confirmed | Network Engineer | 2026-09-08 | Open | Design / Budget
D-001 | Dependency | Basic floor plan is need for project | RFI | Prior to project basic floor plan is need | Follow up | Project Coordinator | TBD | Open | Design
Q-002 | Open Question | Customer has budget for the project |  | Funding limitations may prevent authorization or require reductions to scope, service levels, or implementation approach | Follow up | Project Manager | TBD | Open | Budget
A-003 | Assumption | Local Vendors are available | RFI | Budget rises schedule delays as we will need fly over more people | Labor Recourse Scheduler | Labor Recsourse Manager | TBD | Open | Budget / Schedule
Q-003 | Open Question | Local Vendor Cost | RFI | Cost per hour impact the cost of the budget | Labor Recourse Scheduler | Labor Recsourse Manager | 2026-09-08 | Open | Budget
C-002 | Constraint | Documentation, Knoweldge transfer, handoff | RFI | Project is not completed |  | Project Manager | TBD | Open | Schedule
D-002 | Dependency | Equipment & Material procurment | Scope | Project budget & schedule is haevily dependpent on this activitiy | Procurement Validate all parts have been ordered | Procurement Specialist | TBD | Open | Budget / Schedule
R-002 | Constraint | Network configuration and testing | Scope | Project is delayed as we resolve the issue in the configs | Bandwidth, Ping, Tracesrt test confirm netwokr | Network Engineer | TBD | Open | Schedule
A-004 | Assumption | All procurments arrive on time as schedule |  | Project delays and / or cost increases as we develop new solutions | Products arrive or not | Procurement Specialist | TBD | Open | Budget / Schedule
A-005 | Assumption | Everyone stay well during the project |  | Project delays and / or cost increase as we reassign personnel |  | Project Manager | TBD | Open | Budget / Schedule
Q-004 | Open Question | Are we able to install the network when the school is in session? |  | May impact the budget and recouses needed | Follow up | Project Coordinator | 2026-09-06 | Open | Budget / Schedule